## Road Map
Phase | Phase Name | Step | Step / Deliverable | Status
1 | Foundation & Basic Architecture | 1 | Overall Project Architecture | ✅ Approved
1 |  | 2 | Technology Stack & Project Structure | ✅ Approved
1 |  | 3 | Frontend Architecture — React + TypeScript | ✅ Approved
1 |  | 4 | Backend Architecture — FastAPI | ✅ Approved
1 |  | 5 | AI / Language / Translation Architecture | 🔒 Approved & Locked
1 |  | 6 | PostgreSQL Database Design & Implementation | 🟡 Current
1 |  | 7 | Redis Architecture & Implementation | ⏳ Pending
1 |  | 8 | Authentication & Authorization | ⏳ Pending
1 |  | 9 | User Profile & Language Preference | ⏳ Pending
1 |  | 10 | Language Configuration & Language Management | ⏳ Pending
1 |  | 11 | Chat Room & Group Chat Foundation | ⏳ Pending
1 |  | 12 | Message Management | ⏳ Pending
1 |  | 13 | WebSocket / Real-Time Communication | ⏳ Pending
1 |  | 14 | Local File/Media Storage | ⏳ Pending
1 |  | 15 | Encryption Architecture | ⏳ Pending
1 |  | 16 | Session Management & Account Lifecycle | ⏳ Pending
1 |  | 17 | Basic LangGraph Integration | ⏳ Pending
1 |  | 18 | Basic Agent / Tool / MCP Foundation | ⏳ Pending
1 |  | 19 | Dockerization — Local Development | ⏳ Pending
1 |  | 20 | Frontend + Backend Integration | ⏳ Pending
1 |  | 21 | Phase 1 Testing & Validation | ⏳ Pending
1 |  | 22 | Phase 1 Final Review & Lock | ⏳ Pending
2 | Core Chat Application | 1 | Authentication & User Access Integration | ⏳ Pending
2 | Core Chat Application | 2 | User Registration / Login / Forgot Password | ⏳ Pending
2 | Core Chat Application | 3 | Profile Management | ⏳ Pending
2 | Core Chat Application | 4 | Private Chat | ⏳ Pending
2 | Core Chat Application | 5 | Group Chat — 50+ Users | ⏳ Pending
2 | Core Chat Application | 6 | Online / Offline Presence | ⏳ Pending
2 | Core Chat Application | 7 | Typing Indicator | ⏳ Pending
2 | Core Chat Application | 8 | Message Delivery / Read Status | ⏳ Pending
2 | Core Chat Application | 9 | User Search & Chat Creation | ⏳ Pending
2 | Core Chat Application | 10 | Attachments / Media Handling | ⏳ Pending
2 | Core Chat Application | 11 | Chat History & Message Retrieval | ⏳ Pending
2 | Core Chat Application | 12 | Core Chat Application Validation | ⏳ Pending
3 | Multilingual AI Translation | 1 | Language Configuration Loading | ⏳ Pending
3 |  | 2 | Fast Language Detection | ⏳ Pending
3 |  | 3 | Confidence Evaluation | ⏳ Pending
3 |  | 4 | Language Agent Fallback | ⏳ Pending
3 |  | 5 | Source Language Resolution | ⏳ Pending
3 |  | 6 | Recipient Preferred Language Resolution | ⏳ Pending
3 |  | 7 | Translation Agent | ⏳ Pending
3 |  | 8 | LLM Translation Workflow | ⏳ Pending
3 |  | 9 | Hinglish / Odlish / Mixed-Language Support | ⏳ Pending
3 |  | 10 | Unique Target-Language Translation Optimization | ⏳ Pending
3 |  | 11 | Redis Translation Cache | ⏳ Pending
3 |  | 12 | Translation Latency / Performance Measurement | ⏳ Pending
3 |  | 13 | Multilingual Translation Testing | ⏳ Pending
4 | LangGraph / Agents / Tools / MCP | 1 | LangGraph Workflow Design | ⏳ Pending
4 |  | 2 | Language Agent | ⏳ Pending
4 |  | 3 | Translation Agent | ⏳ Pending
4 |  | 4 | Validation / Routing Agents | ⏳ Pending
4 |  | 5 | Tool Calling Architecture | ⏳ Pending
4 |  | 6 | MCP Server Architecture | ⏳ Pending
4 |  | 7 | Agent State & Workflow Management | ⏳ Pending
4 |  | 8 | Agent Failure / Retry / Fallback | ⏳ Pending
4 |  | 9 | Agent & Tool Execution Tracking | ⏳ Pending
4 |  | 10 | AI Workflow Validation | ⏳ Pending
5 | Security | 1 | Authentication Hardening | ⏳ Pending
5 |  | 2 | Authorization & Room Access Control | ⏳ Pending
5 |  | 3 | Message Encryption at Rest | ⏳ Pending
5 |  | 4 | Encryption Key Management | ⏳ Pending
5 |  | 5 | Secure Message Decryption on Fetch | ⏳ Pending
5 |  | 6 | Session Security & Idle Timeout | ⏳ Pending
5 |  | 7 | Attachment Access Security | ⏳ Pending
5 |  | 8 | Account Deactivation / 30-Day Recovery | ⏳ Pending
5 |  | 9 | Permanent Account Deletion | ⏳ Pending
5 |  | 10 | Security Validation & Audit | ⏳ Pending
6 | Performance & Scaling | 1 | Redis Caching Strategy | ⏳ Pending
6 |  | 2 | Translation Cache Optimization | ⏳ Pending
6 |  | 3 | 50+ User Group Translation Scaling | ⏳ Pending
6 |  | 4 | Concurrent Translation Handling | ⏳ Pending
6 |  | 5 | Background / Queue Processing | ⏳ Pending
6 |  | 6 | WebSocket Scaling | ⏳ Pending
6 |  | 7 | Database Query Optimization | ⏳ Pending
6 |  | 8 | LLM Latency Optimization | ⏳ Pending
6 |  | 9 | Load / Stress Testing | ⏳ Pending
6 |  | 10 | Performance Benchmarking | ⏳ Pending
7 | Docker & AWS Deployment | 1 | Dockerize React Frontend | ⏳ Pending
7 |  | 2 | Dockerize FastAPI Backend | ⏳ Pending
7 |  | 3 | PostgreSQL Deployment Strategy | ⏳ Pending
7 |  | 4 | Redis Deployment Strategy | ⏳ Pending
7 |  | 5 | Local Docker Compose Environment | ⏳ Pending
7 |  | 6 | AWS S3 Attachment Storage | ⏳ Pending
7 |  | 7 | Environment Variables & Secrets | ⏳ Pending
7 |  | 8 | AWS Networking & Security | ⏳ Pending
7 |  | 9 | Container Deployment to AWS | ⏳ Pending
7 |  | 10 | Monitoring / Logging / Health Checks | ⏳ Pending
7 |  | 11 | Production Deployment Validation | ⏳ Pending
8 | Testing & Production Readiness | 1 | Unit Testing | ⏳ Pending
8 |  | 2 | FastAPI API Testing | ⏳ Pending
8 |  | 3 | WebSocket Testing | ⏳ Pending
8 |  | 4 | Database / Integration Testing | ⏳ Pending
8 |  | 5 | Multilingual / Language Detection Testing | ⏳ Pending
8 |  | 6 | Translation Quality Evaluation | ⏳ Pending
8 |  | 7 | Agent / Tool / MCP Testing | ⏳ Pending
8 |  | 8 | Security Testing | ⏳ Pending
8 |  | 9 | Performance Testing | ⏳ Pending
8 |  | 10 | End-to-End Testing | ⏳ Pending
8 |  | 11 | Production Readiness Review | ⏳ Pending
8 |  | 12 | Final Release Approval | ⏳ Pending

## Sheet3
language_code | language_name | native_name | script | variant | is_standard_language | is_user_selectable | is_translation_supported | status
en | English | English | Latin | Standard | TRUE | TRUE | TRUE | ACTIVE
hi | Hindi | हिन्दी | Devanagari | Standard | TRUE | TRUE | TRUE | ACTIVE
hi-Latn | Hindi | हिन्दी | Latin | Hinglish | FALSE | TRUE | TRUE | ACTIVE
bn | Bengali | বাংলা | Bengali | Standard | TRUE | TRUE | TRUE | ACTIVE
bn-Latn | Bengali | বাংলা | Latin | Banglish | FALSE | TRUE | FALSE | ACTIVE
te | Telugu | తెలుగు | Telugu | Standard | TRUE | TRUE | TRUE | ACTIVE
te-Latn | Telugu | తెలుగు | Latin | Tenglish | FALSE | TRUE | FALSE | ACTIVE
mr | Marathi | मराठी | Devanagari | Standard | TRUE | TRUE | TRUE | ACTIVE
mr-Latn | Marathi | मराठी | Latin | Marlish | FALSE | TRUE | FALSE | ACTIVE
ta | Tamil | தமிழ் | Tamil | Standard | TRUE | TRUE | TRUE | ACTIVE
ta-Latn | Tamil | தமிழ் | Latin | Tanglish | FALSE | TRUE | FALSE | ACTIVE
ur | Urdu | اردو | Arabic | Standard | TRUE | TRUE | TRUE | ACTIVE
ur-Latn | Urdu | اردو | Latin | Roman Urdu | FALSE | TRUE | FALSE | ACTIVE
gu | Gujarati | ગુજરાતી | Gujarati | Standard | TRUE | TRUE | TRUE | ACTIVE
gu-Latn | Gujarati | ગુજરાતી | Latin | Guglish | FALSE | TRUE | FALSE | ACTIVE
kn | Kannada | ಕನ್ನಡ | Kannada | Standard | TRUE | TRUE | TRUE | ACTIVE
kn-Latn | Kannada | ಕನ್ನಡ | Latin | Kanglish | FALSE | TRUE | FALSE | ACTIVE
ml | Malayalam | മലയാളം | Malayalam | Standard | TRUE | TRUE | TRUE | ACTIVE
ml-Latn | Malayalam | മലയാളം | Latin | Manglish | FALSE | TRUE | FALSE | ACTIVE
or | Odia | ଓଡ଼ିଆ | Odia | Standard | TRUE | TRUE | TRUE | ACTIVE
or-Latn | Odia | ଓଡ଼ିଆ | Latin | Odlish | FALSE | TRUE | FALSE | ACTIVE
pa | Punjabi | ਪੰਜਾਬੀ | Gurmukhi | Standard | TRUE | TRUE | TRUE | ACTIVE
pa-Latn | Punjabi | ਪੰਜਾਬੀ | Latin | Roman Punjabi | FALSE | TRUE | FALSE | ACTIVE
as | Assamese | অসমীয়া | Assamese | Standard | TRUE | TRUE | TRUE | ACTIVE
mai | Maithili | मैथिली | Devanagari | Standard | TRUE | TRUE | FALSE | ACTIVE
sat | Santali | ᱥᱟᱱᱛᱟᱲᱤ | Ol Chiki | Standard | TRUE | TRUE | FALSE | ACTIVE
ks | Kashmiri | कॉशुर | Devanagari | Standard | TRUE | TRUE | FALSE | ACTIVE
ks-Arab | Kashmiri | کٲشُر | Arabic | Standard | FALSE | TRUE | FALSE | ACTIVE
sd | Sindhi | सिन्धी | Devanagari | Standard | TRUE | TRUE | FALSE | ACTIVE
sd-Arab | Sindhi | سنڌي | Arabic | Standard | FALSE | TRUE | FALSE | ACTIVE
doi | Dogri | डोगरी | Devanagari | Standard | TRUE | TRUE | FALSE | ACTIVE
brx | Bodo | बड़ो | Devanagari | Standard | TRUE | TRUE | FALSE | ACTIVE
mni | Manipuri | মৈতৈলোন্ | Bengali | Standard | TRUE | TRUE | FALSE | ACTIVE
mni-Mtei | Manipuri | ꯃꯤꯇꯩ ꯂꯣꯟ | Meitei Mayek | Standard | FALSE | TRUE | FALSE | ACTIVE
ne | Nepali | नेपाली | Devanagari | Standard | TRUE | TRUE | TRUE | ACTIVE
kok | Konkani | कोंकणी | Devanagari | Standard | TRUE | TRUE | FALSE | ACTIVE
kok-Latn | Konkani | Konkani | Latin | Roman Konkani | FALSE | TRUE | FALSE | ACTIVE
sa | Sanskrit | संस्कृतम् | Devanagari | Standard | TRUE | TRUE | TRUE | ACTIVE

## Sheet1
ID | Task Name | Status | Remarks
6.1 | Requirements | Done
6.2 | Architecture | Done
6.3 | Languages | Done
6.4 | Users | Done
6.5 | Chat Rooms | Done
6.6 | Room Members | Done
6.7 | Messages | Done
6.8 | Translations | Done
6.9 | Message Status | Done
6.1 | Sessions | Done
6.11 | Attachments | Done
6.12 | Agent Executions | Done
6.13 | Tool Executions | Done
6.14 | Relationships/FKs | Done
6.15 | Constraints/Indexes | Done
6.16 | Lifecycle/Triggers | Done
6.17 | Security | Next | Who are the users were avail the access of tables and all so these can be park for now
6.18 | Data Integrity | Done | ¦ # ¦ Issue ¦ Solution ¦ Layer ¦ ¦ -- ¦ -------------------------------------- ¦ --------------------------------------------------------------------- ¦ ---------- ¦ ¦ 1 ¦ Deactivated user sending messages ¦ Backend checks account status before creating message ¦ 🔵 Backend ¦ ¦ 2 ¦ Deactivated room creator ¦ Backend prevents inactive user from creating rooms ¦ 🔵 Backend ¦ ¦ 3 ¦ Deactivated user remaining room member ¦ Backend changes membership to `LEFT`/`REMOVED` during deactivation ¦ 🔵 Backend ¦ ¦ 4 ¦ Message status user not in room ¦ Add composite FK/design relationship to enforce membership ¦ 🟢 DB ¦ ¦ 5 ¦ Attachment uploader not in room ¦ Backend validates uploader is a room member ¦ 🔵 Backend ¦ ¦ 6 ¦ Agent execution user/message mismatch ¦ Backend validates execution context ¦ 🔵 Backend ¦ ¦ 7 ¦ Session lifecycle inconsistency ¦ Backend/scheduler manages expiration/revocation; DB checks timestamps ¦ 🟡 Both ¦ ¦ 8 ¦ `DEACTIVATED` without `deactivated_at` ¦ Add DB CHECK constraint ¦ 🟢 DB ¦ ¦ 9 ¦ Invalid deletion scheduling ¦ Add DB CHECK constraints for scheduling relationship ¦ 🟢 DB ¦ ¦ 10 ¦ Deleted sender becoming NULL ¦ Keep `ON DELETE SET NULL`; this is intentional for message retention ¦ 🟢 DB ¦
6.19 | Soft Delete/Retention | Done | ¦ Area ¦ Decision ¦ ¦ --------------------------- ¦ --------------------------------------------------------------------- ¦ ¦ **User account** ¦ Deactivate first, don't immediately delete ¦ ¦ **Deactivation timestamp** ¦ `deactivated_at` records when it happened ¦ ¦ **Deletion scheduling** ¦ `deletion_scheduled_at` determines when permanent deletion can happen ¦ ¦ **Sessions** ¦ Revoke sessions during deactivation ¦ ¦ **Room membership** ¦ Mark membership `LEFT`/`REMOVED`, don't destroy history ¦ ¦ **Messages** ¦ Preserve messages; use `is_deleted` for message deletion ¦ ¦ **Attachments** ¦ Mark `DELETED`; physical storage cleanup handled separately ¦ ¦ **Translations** ¦ Follow parent message retention ¦ ¦ **Message status** ¦ Preserve required history ¦ ¦ **Agent executions** ¦ Preserve execution/audit history ¦ ¦ **Tool executions** ¦ Preserve execution/audit history ¦ ¦ **Permanent user deletion** ¦ Backend/scheduler performs it after retention period ¦ ¦ **Database cascading** ¦ Only use `CASCADE` where child data should genuinely disappear ¦ ¦ **Retention cleanup** ¦ Backend scheduler/job, not PostgreSQL trigger ¦
6.2 | Audit/Compliance | Done | Created audit logs where all the logs will be captured
6.21 | Transactions | Done | No changes required
6.22 | Concurrency | Done | No changes required
6.23 | Query Design | Done | Select query for all the tables
6.24 | Query Optimization | Done
6.25 | Database Testing | Done
6.26 | Migration Strategy | Done
6.27 | Backup/Recovery | Done | Absolutely. Let's do it from the beginning with no alternatives. Run these commands one by one in PowerShell. Step 1 — Remove the old backup Remove-Item .\backup.dump -ErrorAction SilentlyContinue Step 2 — Create the backup docker exec chat_application_DB pg_dump -U chat_app -d chat_app_db -p 32031 -Fc -f /tmp/backup.dump Step 3 — Copy the backup from Docker to your Windows folder docker cp chat_application_DB:/tmp/backup.dump .\backup.dump Step 4 — Check the backup file Get-Item .\backup.dump ¦ Select-Object Name,Length You should see something like: Name Length ---- ------ backup.dump 12345 The exact size doesn't matter; Length must be greater than 0. Step 5 — Create a test restore database docker exec chat_application_DB dropdb -U chat_app -p 32031 --if-exists restore_db Then: docker exec chat_application_DB createdb -U chat_app -p 32031 restore_db Step 6 — Copy the backup back into Docker docker cp .\backup.dump chat_application_DB:/tmp/restore_backup.dump Step 7 — Restore docker exec chat_application_DB pg_restore -U chat_app -p 32031 -d restore_db /tmp/restore_backup.dump There should be no input file does not appear to be a valid archive error. Step 8 — Verify the restored database docker exec -it chat_application_DB psql -U chat_app -p 32031 -d restore_db Now inside PostgreSQL run: SELECT COUNT(*) FROM chat_app.users; Then: SELECT COUNT(*) FROM chat_app.language_configurations; Then: SELECT COUNT(*) FROM chat_app.messages; Exit: \q
6.28 | Production Readiness | Done